## 2013 recommendations
no | Para | Key Recommendation | Primary Owner | Secondary Owner | Priority | Audit action plan | Implementation status as of October 2014 | Target completion date
1 | 28 | UNDP agreed with the recommendation of the Board that it: (a) establish an appropriate quality assurance mechanism to further improve the consistent implementation of the performance indicators; and (b) include appropriate baselines and targets for expected outputs for all its approved projects in the annual workplan and the integrated annual workplan | BPPS | N/A | High | UNDP will pilot a project-level quality assurance system with select Country Offices and then roll it out to all UNDP offices with required training support in 2014/2015 | In Progress | 2015,Q1
2 | 29 | The Board also recommends that UNDP: (a) regularly reconcile performance indicators, baselines and targets contained in the annual workplans and those in the integrated annual workplans; and (b) ensure the timely approval of the annual project workplans | BPPS | RBX | High | (a) UNDP will establish automated data exchange between the Integrated Workplan (IWP) and Annual Workplan (AWP) system; and (b) Regional Bureaux will monitor progress and work with Country Offices on cases of exceptional delay from 2015 onward | In Progress | 2015,Q1
3 | 36 | UNDP agreed with the Board's recommendation that it: (a) work with government counterparts to ensure that the annual workplans are approved in a timely manner; and (b) monitor the progress of project implementation at the country level to avoid delays during implementation | RBX | RBX | High | UNDP will monitor: (a) cases of exceptional delays in approval of Annual Work Plans; and (b) projects with significant start date delays | In Progress | 2015,Q2
4 | 41 | The Board recommends that UNDP review the projects at its country offices to ensure that they cover mainstreamed activities addressing the thematic areas adopted by UNDP | RBX | RBX | Medium | Regional Bureaux will review Country Office plans for supporting the development priorities of their respective programme government as part of the Annual Business Plan review process | In Progress | 2015,Q1
5 | 43 | The Board recommends that UNDP implement projects according to the annual workplans and address deviations from planned implementation in a robust and a timely manner | RBX | RBX | Medium | Regional Bureaux will work with Country Offices (as needed) to ensure project board approval is received for significant deviations from approved workplans | In Progress | 2015,Q4
6 | 49 | UNDP agreed with the recommendation of the Board that it comply with its Financial Regulations and Rules and its Programme and Operational Procedures and Policies and that it continue to build on current efforts to ensure the diligent monitoring by the regional bureaux and the prioritizing of the financial closure of the remaining tranches of identified operationally closed projects | RBX | RBX | High | Regional Bureaux will prioritize remaining cases of projects to be financially closed and monitor progress of cases with significant delays | In Progress | 2015,Q4
7 | 53 | UNDP agreed with the Board recommendation that it ensure that the project completion checklist is used consistently for the financial closure of development projects, including the preparation of final review reports | RBX | RBX | High | Regional Bureaux will work with Country Offices to ensure project completion checklists and final review reports are prepared for projects to be closed in 2014. | In Progress | 2015,Q4
8 | 57 | UNDP agreed with the recommendation of the Board that it prepare and submit the combined delivery reports in a timely manner in compliance with the Programme and Operations Policies and Procedures | RBX | RBX | Medium | Regional Bureaux will establish mechanisms to monitor timeliness of combined delivery report submission by Country Offices | In Progress | 2015,Q4
9 | 63 | UNDP agreed with the recommendation of the Board that it: (a) prepares quarterly progress reports for the country office as required by the Programme and Operations Policies and Procedures; and (b) regularly update the risks log in the Atlas system; and (c) conduct project field visits and prepare and file reports, as required by the Programme and Operations Policies and Procedures | RBX | RBX | Medium | Regional Bureaux will work with Country Offices to monitor and ensure compliance with regard to POPP requirements on project monitoring and updating risk logs in Atlas | In Progress | 2015,Q4
10 | 67 | The Board recommends that UNDP ensure annual workplans are prepared for all projects in Nigeria as required by the UNDP Handbook on Planning, Monitoring and Evaluating Development Results | Nigeria | RBA | Medium | Nigeria Country Office will ensure that more robust planning systems are in place to prepare and revise the AWP, in line with POPP guidance | In Progress | 2014,Q4
11 | 72 | UNDP agreed with the recommendation of the Board that it take appropriate action to include in the audit plans projects that have never been audited but whose cumulative expenses since inception exceed $0.3 million through the revision and clarification of the criteria to be applied and by considering all expenses recorded by the date set for submission of the audit plan | OAI | OAI | Medium | OAI will include the necessary clarifications and revisions to the NGO/NIM audit policy in POPP. The same revisions and clarifications will be included in the next cycle of project audits that will be undertaken in 2015 (to cover expenditure of FY2014) | In Progress | 2014,Q4
12 | 77 | UNDP agreed with the recommendation of the Board that it direct all regional bureaux to work closely with country offices to ensure that the instructions of the Office of Audit and Investigations are complied with and that all audit reports are submitted within the required period or as subsequently agreed with the Office of Audit and Investigation | RBX | RBX | Medium | Regional Bureaux will strengthen mechanisms (as needed) to monitor timely submission of audit reports and follow up with Country Offices on exceptional cases, in consultation with OAI | In Progress | 2015,Q1
13 | 80 | UNDP agreed with the recommendation of the Board that it ensure that regional bureaux set realistic implementation target dates and monitor the implementation of long outstanding audit recommendations (more than 18 months) involving implementing partners | RBX | RBX | Medium | Regional Bureaux will enhance mechanisms (as needed) to monitor implementation of long outstanding audit recommendations involving implementing partners. | In Progress | 2015,Q4
14 | 84 | UNDP agreed with the recommendation of the Board that it review the causes of recurring modified audit opinions and take remedial action, as required, through engaging the regional bureaux and respective implementing partners | RBX | RBX | Medium | Regional Bureaus will work with relevant Country Offices to implement measures, including consideration of alternate cash transfer modalities for NIM projects with three consecutive years of modified audit opinions. | In Progress | 2015,Q4
15 | 91 | UNDP agreed with the recommendation of the Board that it: (a) assess risks surrounding executing the national implementation modality to find out why assurance procedures other than an audit could not detect the suspected irregular procurement procedures and improve controls; and (b) continue engaging with the partner Government to ascertain more facts about the matter in order to establish the actual loss the projects suffered and possibilities of recovery from the individuals involved | RBLAC | RBLAC | High | RBLAC (in consultation with OFRM and OAI) will work with the Country Office to perform the necessary review and assessment; and follow up with the programme Government | In Progress | 2015,Q2
16 | 94 | UNDP agreed with the recommendation of the Board that, unless there is a bilateral agreement with the donor(s) concerned, it make every effort to refund amounts due to donors and clear all balances exceeding 90 days in the 2013 account (refunds pending to donors) as required by the Programme and Operations Policies and Procedures and year-end closure instructions | OFRM | OFRM | High | OFRM will consider additional measures including possible comprehensive clauses in agreements on treatment of unspent balances beyond 90 days | In Progress | 2014,Q4
17 | 101 | UNDP agreed with the recommendation of the Board that it: (a) enforce its guidance notes to country offices on the implementation of the revised harmonized approach to cash transfers framework; and (b) follow-up with regional bureaux and work with country offices to ensure that pending macro- and microassessments for the respective programming cycle are conducted as planned | OFRM | RBX | High | On (a) UNDP will promulgate and monitor compliance with guidance notes to Country Offices. On (b) this an ongoing process. Regional Bureaus will enhance mechanisms for monitoring implementation of macro and microassessments, as required | In Progress | 2015,Q4
18 | 107 | UNDP agreed with the recommendation of the Board that it work with WHO and UNRWA to clarify the propriety of the payable/receivable balances, including references to specific accounting policies (if different from UNDP) when confirming their balances to the Board | OFRM | OFRM | Medium | UNDP will proactively communicate with WHO and UNRWA to confirm accounting polices used & clarify nature of items requiring confirmation at year-end | In Progress | 2015,Q1
19 | 112 | UNDP agreed with the recommendation of the Board that it: (a) develop a consolidated procurement plan in accordance with the programme cycle at the country office; and (b) ensure country offices upload their procurement plans in the repository designed at UNDP headquarters | RBX | PSO | Medium | Regional Bureaux will enhance mechanisms for monitoring the uploading of country-level consolidated procurement plans in the HQ designated repository | In Progress | 2015,Q1
20 | 114 | UNDP agreed with the recommendation of the Board that it ensure that all members of evaluation committees who are non-UNDP staff sign a declaration of impartiality to declare their non-conflict of interest as required under the Programme and Operations Policies and Procedures | RBX | PSO | Medium | Regional Bureaux (in consultation with Procurement Support Office-PSO) will enhance mechanisms to ensure compliance with the requirement | In Progress | 2015,Q3
21 | 117 | The Board recommends that UNDP closely follow up with the implementing partners to ensure that the delivery of goods and services is made without delay and according to the signed contracts; and that the signing of confirmation-of-delivery reports is done in a timely manner | RBX | PSO | Medium | Regional Bureaux (in consultation with PSO) will enhance mechanisms to ensure compliance with the requirement | In Progress | 2015,Q3
22 | 120 | UNDP agreed with the recommendation of the Board that it: (a) ensure that country offices comply with the Service Contract User Guide in relation to the hiring of staff on service contracts and the proper timing of performance evaluations; and (b) review the current service contractor modality and policy, including the nature of project-related work at the country offices and associated service contract performance evaluation requirements | OHR | RBX | Medium | On (a) Regional Bureaux will work with Country Offices concerned to address specific issues identified. On (b) UNDP will review the current Service Contractor policy | In Progress | 2015,Q3
23 | 124 | UNDP agreed with the recommendation of the Board that it review the after-service health insurance funding plan on a regular basis and develop an appropriate funding strategy so that the funding plan remains viable | OFRM | OFRM | Medium | An ASHI funding plan is already in place. UNDP will review the existing funding strategy annually when results of actuary studies are available | In Progress | 2015,Q1
24 | 129 | UNDP agreed with the recommendation of the Board that it review the current Atlas Payroll profiles to restrict the granting of conflicting roles in line with the internal control framework on payroll administration | OHR | OIST | Medium | UNDP will review and revise profiles as needed to meet the workflow requirements within the Benefits and Entitlements Services unit | In Progress | 2015,Q2
25 | 134 | UNDP agreed with the recommendation of the Board that it: (a) institute a rigorous monitoring mechanism to ensure that terminated employees are deactivated in the Atlas system without delay; and (b) consider options to mitigate situations involving future-dated separations to ensure that terminated employees do not have unauthorized access to the Atlas system | OIST | OIST | High | On (a), The communication to ARGUS focal points was improved starting in March 2014, via monthly distribution of Atlas Security Reports to all ARGUS focal points. The Security Reports have been delivered to ARGUS focal points each month since then. This activity partially implements part (a) of the recommendation. Options to make the monitoring mechanisms more rigorous are under discussion. On (b), the ATLAS patch to correctly handle future dated separations has been tested and installed in ATLAS, resolving issue (b). | In Progress | 2014,Q4
26 | 138 | UNDP agreed with the recommendation of the Board that it implement an automated e-mail notification to staff members and their supervisors for approvals of advance leave beyond the approved limit of 10 days. | OHR | OIST | Medium | UNDP will ensure that upon request for advance leave, the Senior Manager and Supervisor concerned will be notified automatically when applying through eServices | In Progress | 2015,Q1
27 | 141 | UNDP agreed with the recommendation of the Board that it ensure that country offices establish updated disaster recovery plans and utilize them | BOM Directorate | RBX | Medium | Regional Bureaux (in collaboration with Bureau of Management) will enhance mechanisms to monitor implementation of updated disaster recovery plans with specific priority on countries with special development needs/risk | In Progress | 2015,Q2
28 | 144 | UNDP agreed with the recommendation of the Board that it: (a) monitor the uploading of inventory certificates to ensure that it is done in a timely manner; (b) monitor and control reports from the country offices and attend to issues raised in those reports; and (c) deal with exceptional cases of delayed submissions by the country offices | OFRM | OFRM | Medium | UNDP will enhance mechanisms for monitoring timeliness of inventory certification uploads and ensure necessary follow up as required as part of the year-end closing process | In Progress | 2015,Q2