COSTED EVALUATION PLAN

Country: 	Seychelles

CPD Period:  	2012 – 2016

| CPD Outcome | Strategic Plan Results Area | Evaluation Title | Partners (joint evaluation) | Evaluation commissioned by (if not UNDP) | Type of evaluation | Planned Evaluation Completion Date | Estimated Cost (USD) | Provisional Source of Funding |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Capacities of the Social Welfare Agency and the National Bureau of Statistics strengthened to promote the establishment and regular monitoring of a national poverty line leading to a better targeting of social welfare programmes in Seychelles | Poverty Reduction and MDG achievement | Evaluation of the contribution of UNDP’s programme in support of the social welfare strategies in Seychelles | Social Welfare Agency Government of Seychelles National Bureau of Statistics | UNDP | Outcome Evaluation (as part of the final CPD Evaluation) | December 2015 | 10,000 | Development Support Services |
| By 2016, the governance systems, use of technologies and practices and financing mechanisms that promote environmental, energy and climate change adaptation have been mainstreamed into national development plans. | Environment and Sustainable Development | Evaluation of the contribution of UNDP’s environmental programme in Seychelles | Department of Environment/ GEF Programme Coordinating Unit/ GEF Regional Coordinating Unit (Pretoria) | UNDP | Outcome Evaluation (as part of the final CPD Evaluation) | December 2015 | 10,000 | Development Support Services/GEF |
| Mid-term Review of CPD | All | Mid-term review | Government of Seychelles | UNDP | Other | December 2014 | 10,000 | Development Support Services |
| Final CPD Evaluation | All | End of cycle Evaluation | Government of Seychelles | UNDP | Programme Evaluation (including two outcome evaluations) | December 2015 | 10,000 | Development Support Services |
| Project Evaluations |  |  |  |  |  |  |  |  |
| Strengthening Seychelles Protected Areas System through NGO Management | Environment and Sustainable Development | Mid Term Evaluation for the GEF Project | Department of Environment/ GEF Programme Coordinating Unit GEF Regional Coordinating Unit (Pretoria) | GEF | Mandatory Project Evaluation | July 2013 | 10,000 | GEF Project Funds |
| Mainstreaming Biodiversity into Production Sectors and Landscapes | Environment and Sustainable Development | Final Evaluation for GEF Project | Department of Environment/ Department of Environment /GEF Programme Coordinating Unit/ GEF Regional Coordinating Unit (Pretoria) | GEF | Mandatory | July 2014 | 10,000 | GEF Project Funds |
| Mainstreaming Prevention and Control Measures for Invasive alien Species into Trade, Transport and Travel across the Production Landscape (Biosecurity Project) | Environment and Sustainable Development | Final Evaluation of GEF Project | Department of Environment /GEF Programme Coordinating Unit/ GEF Regional Coordinating Unit (Pretoria) | GEF | Mandatory | July 2014 | 10,000 | GEF Project Funds |
| SEYCHELLES/Governance Capacity Building Programme | Democratic Governance | Mid-Term Evaluation for EU Funded Project | European Union Ministry of Foreign Affairs UNDP/ Liaison Unit for NGOs (LUNGOS) | EU | Mandatory as per Contributions Agreement | September 2012 | 30,000 | EU Funds |
| Capacity Development for Improved National and International Environmental Management in Seychelles | Environment and Sustainable Development | Mid Term Evaluation | Department of Environment /GEF Programme Coordinating Unit/ GEF Regional Coordinating Unit (Pretoria) | GEF | Mandatory | July 2012 | 7,000 | GEF Funds |