**Evaluation Plan – Gabon CPD (2023-2027)**

**APPENDIX. BUDGETED EVALUATION PLAN**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **#** | **UNSDCF (or equivalent)****Outcome**  | **UNDP Strategic Plan Outcome** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if not UNDP)** | **Type of evaluation** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| 1 | **Outcome 1:** The legal and institutional framework is strengthened, and institutions are more accountable, transparent and efficient, ensuring inclusive governance and sustainable and equitable development in line with Gabon's national and international commitments (All 17 SDGs)And **Outcome 2**: By 2027, populations, especially youth and women, participate in the sustainable management of natural resources and benefit from the fruits of a controlled transition to a green and blue economy in an environment more resilient to climate change (SDGs 1, 5, 6, 8, 9, 10, 11, 12, 13, 14, 15, 17) | Outcomes 1 & 2 | CPD mid-term evaluation | * Ministries of Environment, Economy, Budget
* RCO
* ANPN
* CNC
 | UNDP | CPD Evaluation | April 2025 | USD 40,000 | TRAC1 |
| 2 | Outcome 2: By 2027, populations, especially youth and women, participate in the sustainable management of natural resources and benefit from the fruits of a controlled transition to a green and blue economy in an environment more resilient to climate change (SDGs 1, 5, 6, 8, 9, 10, 11, 12, 13, 14, 15, 17) | Outcome 1 | Evaluation of the Outcome 2 | * Ministries of Environment, Economy, Budget
* RCO
* ANPN
* CNC
 | UNDP | Outcome Evaluation | August 2026 | USD30,000 | Co-financing with Project funding |
| 3 | Outcome 1: The legal and institutional framework is strengthened, and institutions are more accountable, transparent and efficient, ensuring inclusive governance and sustainable and equitable development in line with Gabon's national and international commitments (All 17 SDGs)And Outcome 2: By 2027, populations, especially youth and women, participate in the sustainable management of natural resources and benefit from the fruits of a controlled transition to a green and blue economy in an environment more resilient to climate change (SDGs 1, 5, 6, 8, 9, 10, 11, 12, 13, 14, 15, 17) | Outcomes 1 & 2 | Thematic evaluation: Youth and Women Inclusion | * Ministry of Economy and Budget
 | UNDP | Thematic evaluation | February 2026 | USD 30,000 | Co-financing with Project funding |
| 4 | Outcome 2: By 2027, populations, especially youth and women, participate in the sustainable management of natural resources and benefit from the fruits of a controlled transition to a green and blue economy in an environment more resilient to climate change (SDGs 1, 5, 6, 8, 9, 10, 11, 12, 13, 14, 15, 17) | Outcome 1 | Mid-term evaluation of the GEF project: “*Transforming Forest Landscape Governance in the Lower Ogooué – Lower Nyanga Landscape Corridor, Gabon*” | * Ministry of the Environment
* ANPN
* CNC
* GEF
 | UNDP | Project evaluation | July 2025 | USD 25,000 | Project funding |
| 5 | Outcome 2: By 2027, populations, especially youth and women, participate in the sustainable management of natural resources and benefit from the fruits of a controlled transition to a green and blue economy in an environment more resilient to climate change (SDGs 1, 5, 6, 8, 9, 10, 11, 12, 13, 14, 15, 17) | Outcome 1 | Final GEF Project Evaluation: “*Transforming Forest Landscape Governance in the Lower Ogooué – Lower Nyanga Landscape Corridor, Gabon*” | * Ministry of the Environment
* ANPN
* CDC
* CNC
* GEF
 | UNDP | Project evaluation | July 2027 | USD 30,000 | Project funding |
| 6 | Outcome 2: By 2027, populations, especially youth and women, participate in the sustainable management of natural resources and benefit from the fruits of a controlled transition to a green and blue economy in an environment more resilient to climate change (SDGs 1, 5, 6, 8, 9, 10, 11, 12, 13, 14, 15, 17) | Outcome 1 | Final project evaluation: «*CAFI 3 : Offrir aux populations urbaines des possibilités d'éducation et d'accès aux jardins forestiers et aux parcs urbains* » | * Ministries in charge of the Environment, Economy, Budget
* RCO
* UNESCO
* ANPN
* CNC
 | UNDP | Project evaluation | September 2027 | USD 30,000 | Project funding |