**FULLY-COSTED EVALUATION PLAN**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **UNSDCF** **Outcome**  | **UNDP Strategic Plan Outcome** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by** **(if not UNDP)** | **Type of evaluation** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| **UNSDCF OUTCOME INVOLVING UNDP #3.2:** People in Iraq, civil society and communities, particularly women, have improved capacity to lead, participate in and contribute to the design and delivery of equitable and responsive services, especially for the most vulnerable populations. | **Outcome 2:** Accelerate structural transformations for sustainable development | Final Evaluation: Support to Integrated Reconciliation to Iraq | Prime Minister’s Office, Co-existence and Community Peace Committee, Iraqi Council of Representatives (CoR), Council of Minister’s Secretariat (COMSEC), Ministry of Labour and Social Affairs,  | UNDP  | Project Evaluation | December 2022 | $35,000 | Project budget |
| Final Evaluation- Stabilization | Council of Minister’s Secretariat (COMSEC), Governorate Offices, Stabilization Steering Committee, UNMAS, UNHABITAT,Civil Society Organizations | UNDP | Thematic Evaluation | March 2020 | $350,000 | Project Budget  |
| **UNSDCF OUTCOME INVOLVING UNDP #2.1:** Improved people-centred economic policies and legislation contribute to inclusive, gender sensitive and diversified economic growth, with focus on increasing income security and decent work for women, youth and vulnerable populations. | **Outcome 1:** Advance poverty eradication in all its forms and dimensions | Final Evaluation: Funding Facility for Economic Reform – Kurdistan Regional Government (KRG) | Ministry of Planning and Relevant Ministries and Boards in the Kurdistan Regional Government | UNDP  | Project Evaluation | September 2020 | $35,000 | Project Budget  |
| Final Evaluation: Funding Facility for Economic Reform – Federal | Ministry of Planning, and Relevant Ministries and Boards | UNDP  | Project Evaluation | September 2020 | $35,000 | Project Budget  |
| Mid-Term Evaluation: Support to Recovery and Stability through Local Development in Iraq | Ministry of Planning- GoI and KRG, Governorates of Anbar, Salahadin and Ninewah, Basra, Missan, ThiQar, Erbil, Suly Dohuk  | UNDP  | Project Evaluation |  June 2021 | $30,000 | Project Budget  |
| Final Evaluation: Support to Recovery and Stability through Local Development in Iraq | Ministry of Planning- GoI and KRG, Governorates of Anbar, Salahadin and Ninewah, Basra, Missan, ThiQar, Erbil, Suly Dohuk  | UNDP  | Project Evaluation | June 2023 | $ 30,000 | Project Budget  |
| Evaluation: Support to Recovery and Stability through Local Development in Iraq | Ministry of Planning- GoI and KRG, Governorates of Anbar, Salahadin and Ninewah, Basra, Missan, ThiQar, Erbil, Suly Dohuk  | European Union | Donor Commissioned Project Evaluation  | October 2023 | $30,000 | Donor Funded |
| **UNSDCF OUTCOME INVOLVING UNDP #3.1:** Strengthened institutions and systems deliver people-centred, evidence- and needs-based equitable and inclusive gender- and age-responsive services, especially for the most vulnerable populations, with particular focus on advocating for women’s leadership in decision-making processes. | **Outcome 2:** Accelerate structural transformations for sustainable development | Mid-Term Evaluation: Support to Security & Justice Sector Governance in Post- Conflict Iraq |  Ministry of Interior, National Police Affairs Agency, Higher Judicial Council, Office of National Security Advisor, Parliamentary Security and Defense Committee. | UNDP | Project Evaluation | July 2020 | $35,000 | Project budget |
| Final Evaluation: Support to Security & Justice Sector Governance in Post- Conflict Iraq | Ministry of Interior, National Police Affairs Agency, Higher Judicial Council, Office of National Security Advisor, Parliamentary Security and Defense Committee | UNDP | Project Evaluation | September 2021 | $35,000 | Project budget |
| **UNSDCF OUTCOME INVOLVING UNDP #4.1:** Strengthened and resourced policies and frameworks are implemented for managing natural resources (including trans-boundary issues), developing renewable resources, and increasing resilience to climate change, environmental stress and natural hazards, and man-made and natural disasters. | **SP Outcome 2:**  Accelerate structural transformations for sustainable development | Final Evaluation- Mosul Dam Emergency Preparedness Project (MDEP) | Prime Minister National Operation center (PMNOC), Prime Ministers Advisory Council (PMAC) | UNDP | Project Evaluation | February 2021 | $50,000  | Project Budget  |
| Final EvaluationGlobal Climate Fund (GCF) Readiness | Ministry of Health & Environment | UNDP | Project Evaluation | 30 April 2020 | $35,000 | GCF Budget |
| **UN Sustainable Development Cooperation Framework (UNSDCF)** | Not Applicable | Final Evaluation-UNSDCF  | UNCT | UNCT | UNSDCF Evaluation | 2023 | UNCT Cost-Shared | UNCT Cost-Shared |