**ANNEX**. **FULLY-COSTED EVALUATION PLAN 2023 - 2025**

The UNDP Lebanon Evaluation Plan is an important accountability and learning instrument for the Country Office, project teams, and stakeholders. It is designed as a strategic tool to inform decision-making at both programme and project levels as well as future programming and achievement of UNDP Strategic Plan 2022-2025 goals. Moreover, the evaluation plan will support programme and project staff as well as stakeholders better understand and respond to the rapidly changing political, social, environmental, and economic dynamics in the country.

This evaluation plan consists of a combination of outcome and project level evaluations representative of the Country Programme Document 2023-2025. The evaluation plan will be coordinated by a newly created central Country Office MEL capacity. Outcome level evaluations have been added to support senior management and programme staff understanding of how UNDP is contributing to the UNSCDF outcomes, with Outcome 3 being evaluated in the midterm to allow time for programme staff to adjust programming, if needed, to the changing circumstances and Outcome 2 being evaluated at the end for programme staff to incorporate learning in the next programme document cycle. A thematic evaluation has been added in Q2 of 2025 to assess all outcomes contributions to gender equality and women empowerment in order to integrate learning into the next Country Programme Document.

It is important to note that all mandatory evaluations as per the evaluation guidelines are included and that risks and challenges that hinder evaluation implementation will be taken into consideration through mitigation measures during annual reviews. The plan will be revised on annual basis. For future projects approved within the framework of the new cycle, relevant evaluations will be integrated in the Evaluation Plan as they arise, in compliance with UNDP regulations.

| **UNSCDF** | **UNDP SP** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by** | **Type of evaluation** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Outcome** #3: Strengthened stabilization and green recovery to reduce vulnerabilities and environmental risks, including through enhanced competitiveness and business environment of sustainability-oriented MSMEs and high potential green productive sectors' values chains. | **STRATEGIC PLAN OUTCOME 2:** No one left behind, centering on equitable access to opportunities and a rights-based approach to human agency and humandevelopment. | Land degradation neutrality in Mountain areas |  | UNDP | Final project evaluation | Dec-24 | 20,000 | GEF |
| Sustainable Transport |  | UNDP | Midterm project evaluation | Nov-24 | 20,000 | GEF |
| Capacity Building Initiative for Transparency |  | UNDP | Terminal project evaluation | Jan-25 | 20,000 | GEF |
| Towards a Decentralised Waste Management Integrated Response (TaDWIR) in Lebanon |  | UNDP | Midterm project evaluation | Dec-23 | 50,000 | EU |
| Outcome #3 evaluation |  | UNDP | Midterm Programme Outcome Evaluation | Dec-24 | 60,000 | UNDP |
| **Outcome** #2 - Strengthened security, stability, justice, and social peace. | **STRATEGIC PLAN OUTCOME 3:** Resilience built to respond to systemic uncertainty and risk. | Tension Monitoring System Evaluation | UNDP and Social Stability and Tension Task Force including UNHCR | UNDP | Midterm Project evaluation | Jan-23 | 40,000 USD | TMS funding (split between donors) |
| Enhancing Community Security and Access to Justice in Lebanese Host Communities |  | UNDP | Midterm project evaluation | Dec-24 | 20,000 USD | Canada |
| Peace Building in Lebanon |  | UNDP | Midterm project evaluation | Dec-24 | 20,000 USD | KFW |
| Outcome #2 evaluation |  |  | Terminal  Programme Outcome Evaluation | Mar-25 | 60,000 | UNDP |
| **Outcome** #1 - Strengthened inclusive social contract grounded in human rights to enhance good governance, effective and accountable institutions, and women's participation. | **STRATEGIC PLAN OUTCOME 1:** Structural transformation accelerated, particularly green, inclusive, and digital transitions. | Anti-Corruption for Trust in Lebanon |  | UNDP | Final project evaluation | 25-Dec | 25,000 USD | EU-DANIDA |
| Lebanese Electoral Assistance Project |  | UNDP | Final project evaluation | Oct-23 | 40,000 USD | EU |
| Integrating Gender into Lebanese Institutions |  | UNDP | Final project evaluation | Mar-23 | 20,000 USD | CND |
| Terminal Gender Impact Evaluation to assess contribution of all outcomes to gender equality and women empowerment |  | UNDP | Terminal programme thematic evaluation | Mar-25 | 60,000 USD | UNDP |