### Country:		[Pakistan]

### COUNTRY PROGRAMME PERFORMANCE SUMMARY

### Reporting period: 	[2018-2022]

### I.  EXECUTIVE SUMMARY

Pakistan’s UNDP Country Programme 2018 - 2022 was executed at a time when the country was confronting numerous problems. Although the 2018 general elections resulted in a peaceful transition, the newly constituted administration was plagued with a debt problem and a trade imbalance. Following the 2018 elections, 20.5 percent of women were elected to the parliament (National Assembly) (CPD Outcome 1). Pakistan achieved progress in reporting SDG statistics, due to UNDP’s assistance in creating SDG Units at the national and provincial levels. UNDP’s technical assistance also enabled the provinces to formulate the SDG national and sub-national frameworks (CPD Outcome 1). In 2021, the government was also able to enact the Elections (Second Amendment) Bill, which gave nine million overseas Pakistanis voting rights and also allowed people to vote using electronic voting machines in the general elections of 2023. In Khyber Pakhtunkhwa, the government was also able to hold the long-awaited local government elections towards the end of 2021 (CPD Outcome 1) With UNDP’s support, the government was able to reach out to 1,004,306 marginalised persons, more than half of whom were women, for livelihood and income opportunities. (CPD Outcome 2)

During the implementation of Country Programme 2018 - 2022, 1.8 million hectares of land was protected through landscape management, biodiversity conservation and land delineation. 697 metric tonnes of persistent organic pollutant chemicals were inventoried, and 286 metric tonnes of hazardous materials were disposed. (CPD Outcome 2) Seven women-led organizations were included in the SGP 6 initiative, out of 38 grants, with 50 percent of the grants benefiting women directly through various activities. The UNDP’s projects in the CPD 2018-2022 were well linked with the development priorities of the Government. It also aided UNDP’s position as a vital player in advancing the climate change and disaster risk reduction agenda.

Pakistan’s issues persisted in the areas of human development and eliminating inequities, such as gender inequality, women’s empowerment, and youth empowerment. In addition, the country made little progress in terms of gender equality and human development. Pakistan was ranked 153rd out of 156 countries on gender inequality matrix in the World Economic Forum’s Global Gender Gap report 2021. Pakistan was also ranked 154 out of 189 countries in 2021, with HDI of 0.557 up from 0.570 in 2020. Due to the COVID-19 pandemic, the country will continue to face economic and fiscal challenges. It will stifle progress and development gains from economic activity prior to the outbreak. This will have an impact on the government’s efforts to mainstream and report on SDGs through institutional mechanisms. From 2000 - 2019, Pakistan was ranked among the top ten most affected countries in the long-term climate risk index from 2000 to 2019. This signifies the need to continue support in the areas of disaster management and climate risk reduction in Pakistan, as well as the need to strengthen institutional mechanisms in the future to realize the benefits of the Country Programme 2018 - 2022 interventions.

### II: Country Programme Performance Summary

| Country information |  |  |  |  |
| --- | --- | --- | --- | --- |
| Country name: Pakistan |  |  |  |  |
| Current country programme period: 2018-2022 |  |  |  |  |
| Outcomes |  | Total Expenditure | Key Indicators of outcome (1-4 per outcome) | Progress made against key indicators |
| 1. Increased effectiveness and accountability of governance mechanisms. |  | 45.79 $ million of the budget of 97.27 $ million | - Extent to which post 2015 agenda and the Sustainable Development Goals are integrated and adapted into national development plans and budgets - Access to justice services disaggregated by sex and population group - Extent to which there is open access to data on government budgets, expenditures, and public procurement - Proportion of women to men in parliament | - In 2020, 80 SDG indicators were reported compared to 36 in 2018 (122 percent increase). - Legal services were provided to 372 men and 905 women (71 percent) in Khyber Pakhtunkhwa. - No data is available - Women make up 20.5 percent of the Parliament (National Assembly) (In the footnote, there is a comparison to the global percentage of women parliamentarian). |
| UNDP Contribution: CP Outputs: The UNDP CP identified three major outputs to support the Government in achieving this outcome: (a) Democratic governance of state institutions, including Parliament, provincial assemblies, local governments and electoral management bodies, strengthened to be responsive to citizens and accountability, for improved service delivery; (b) Strengthened functioning, financing and institutional capacities facilitate access to justice and improve redress mechanisms by the rule of law institutions; and (c) Through active citizen engagement, national/provincial governments shape public policy priorities and establish planning, financing and monitoring mechanisms, facilitating implementation of the Sustainable Development Goals. Progress and Achievements: People’s perceptions of legal services in Pakistan have improved as a result of UNDP’s support to developing institutional capacities of governance structures. In KP, 89 percent of respondents said UNDP interventions had improved women’s access to the legal system, while 87 percent said police service had improved as a result of UNDP contributions. The UNDP’s technical assistance to the Election Commission of Pakistan’s ‘Gender and Disability Electoral Working Group’ facilitated consultations on women, persons with disabilities, and transgender people’s participation in the electoral process. The United Nations Development Programme (UNDP) contributed to the passage of the ‘Local Government (LG) Amendment Bill, 2019’. The 36 indicators were monitored in 2018 owing to UNDP’s support at the provincial and federal levels. In 2019, a total of 51 SDG indicators were tracked across 15 goals (42 percent increase). UNDP’s contribution to the development of the SDG dashboard in 2020 ensured reporting on 80 SDG indicators (57 percent increase compared to 2019). The development expenditure may now be tracked at the national and subnational levels due to technical assistance in building an expenditure tracking system. With UNDP’s technical assistance, all provinces were able to develop their national and sub-national SDG frameworks. Pakistan was also able to present its first SDG Investments Report to the Global Investors for Sustainable Development (GISD) alliance in New York with the UNDP’s technical assistance. The UNDP built the capacity of key governance actors such as the Pakistan Election Commission, Social Welfare Departments, and the District administrations at the national and provincial levels. The UNDP assisted the government in strengthening governance mechanisms, (SDGs 1,5,10,13, and 16). With UNDP’s support, 144,458 women in KP were able to register for local government elections. Through awareness sessions and outreach material on COVID-19 SOPs for by-elections in 2021, a total of 69,500 voters (49 percent of whom were women) were reached. The federal and provincial governments were able to map their Annual Development Plans to SDG targets with the help of UNDP. The project also completed a data gap study with the Bureaux of statistics across the board. SDG frameworks were created for all provinces, with baselines set as well. Balochistan Sustainable Development Goals Unit was in charge of drafting the Balochistan Comprehensive Development and Growth Strategy document. Inter-provincial conferences on issues such as the local government and human rights were also formed by the UNDP. |  |  |  |  |
| 2. Enhanced resilience and socioeconomic development of communities. | 60.90 $ million of the budget of 146.16 $ million |  | - Hectares of land that are managed sustainably under a conservation, sustainable-use or access-and-benefits-sharing regime - Economic loss from disasters as a proportion of the exposed gross domestic product | - In Punjab, Sindh, KP, and GB, improved management and demarcation methods resulted in the conservation of 1.8 million hectares of land. - No data is available. (In the footnote, economic losses per unit GDP attributable to climate risk are mentioned) |
| UNDP Contribution: CP Outputs: The UNDP CP identified three outputs for this outcome: a) National and provincial policies, systems and institutions enabled to achieve structural transformation and promote inclusive economic, social and political opportunities; b) Revitalized productive capacities are sustainable and generate employment opportunities and improvement in sustainable livelihoods as part of broader development efforts; and c) Legal and regulatory frameworks and policies are in place, and institutions capacitated for the conservation, sustainable use, inclusive access and benefit-sharing of natural resources, biodiversity, chemicals, waste management and ecosystems. Progress and Achievements: The government has generated a set of policies related to climate change and adaptation. Updated National Climate Change Policy (draft in 2021), updated Nationally determined Contributions (NDCs) document (2021), and Climate Change Action Plans at the provincial level (2021) are some of the policies that UNDP has supported. UNDP also revised and finalized the national climate change action plan, providing technical support to enable district disaster response teams to conduct their own assessments of early recovery needs. UNDP assisted the governments of Sindh and KP in formulating landscape management plans. It also aided the government of KP by providing a management information system for forest monitoring. The United Nations Development Programme (UNDP) conducted a number of innovative interventions to help women. Women on Wheels was one such effort that aided in the empowerment of female drivers, the creation of new work opportunities, and the mobilisation of service providers to hire them. Furthermore, giving remote healthcare service training to women doctors enabled these doctors to participate in telehealth services. In KP, Sindh, and Balochistan, UNDP’s youth engagement galvanised young people to work on issues such as women’s rights, peace, and security. Women entrepreneurs who were given digital training were able to run their small businesses successfully. UNDP also collaborated with the Prime Minister’s Kamyab Jawan Programme to provide young entrepreneurs with subsidised business loans. The Government committed PKR 46 million for climate change programmes in the 2019 - 2020 budget, which was nine times more than the allocation for 2018-2019. This demonstrates the government’s commitment to working on climate risk mitigation and related concerns. The UNDP’s interventions were also in line with the government’s focus on climate risk mitigation. 1.8 million hectares of land was saved through rehabilitation, land delineation, sustainable practices, bio diversity conservation, and improved management in KP, Punjab, Sindh and GB. UNDP also assisted in the inventorying of 607 metric tonnes of Persistent Organic Pollutant Chemicals in AJK, GB, and KP as well as the safe disposal of 286 metric tonnes of hazardous materials. UNDP also assisted the government in reducing 50 percent from a total of 248.11 Ozon depleting potential (ODP) tonnes. The SFM project’s community forest management trainings attracted 57 percent women participation, exceeding the planned target of 10 percent women’s participation. More than half of the awarded grants in the ‘6th Operational Phase of the GEF Small Grants Programme in Pakistan (SGP 6)’ provided direct benefit to women, with activities ranging from energy efficient stoves to mangrove forest protection. (UNSDF, Outcome 2). |  |  |  |  |

Summary of evaluation findings (e.g. from outcome and project evaluations, UNDAF reviews, and other assessments) Effectiveness and Efficiency: The UNDP, in collaboration with FAO, UNICEF, and UN Women, assisted the government in the political, administrative and fiscal mainstreaming of newly merged districts (previously the FATA region) in KP. Over USD 50 million was raised from bilateral and multilateral sources by UNDP (i.e., Green Climate Fund, USAID, Government of Japan and the Government of Norway). It has also secured USD 10.5 million from the European Union and USD 1.4 million from the Italian government for its ‘Rule of Law’ initiative in Khyber Pakhtunkhwa. UNDP was also able to secure USD 6.7 million from the Global Environment Facility (GEF). UNDP also formed partnerships with the public and private sectors, including mobile service providers (Telenor and Jazz), bottlers (PepsiCo), banks (Citi Foundation), NGOs (Hashoo Foundation), and the government’s ‘Ignite Fund’ and ‘National Incubation Center’, to help young entrepreneurs, particularly women, grow their business. Women’s participation was ensured by UNDP’s engagement with local partners, i.e., Gawadar Institute of Technology (GIT) and Institute of Business Administration (IBA), which helped the programme reach 25% women through technical & vocational training at GIT and 50% women through entrepreneurship training at IBA. According to previous tracer studies by these institutions, more than 50% of the trained youth have either launched their own business or found work. Community empowerment has been aided by UNDP’s assistance for community-based organisations (CBOs), notably women-led organisations. This has not only aided innovation, but has also assisted in the creation of livelihood options for marginalised people, particularly those who are likely to be impacted by climate change. Ministry of Climate Change, Ministry of Human Rights, National Disaster Management Authority, Provincial Disaster Management Authorities, Pakistan Meteorological department, Forest department and District administration, Non-Governmental Organizations, and Community Based Organizations, Corporate partners and Academia were among the stakeholders with whom UNDP developed partnerships at the provincial and national levels. UNDP’s involvement aids in the development of departments’ capacity to oversee disaster risk reduction and climate change adaptation initiatives. This has aided UNDP’s status as a vital player on the ground. The UNDP worked with a number of partners to highlight important development issues. It engaged with UNICEF to raise awareness about child poverty, with WHO to work on health-related SDG indicators, and with Sightsavers, an International charity, to translate the SDG goals and indicators into braille for people with disabilities. During the implementation of the CPD 2018 – 2022, UNDP was able to scale up its governance, rule of law, and community resilience programmes in Pakistan due to multilateral funding from UKAid, USAID and German government. Key Achievements: During the implementation of CPD 2018 – 2022, UNDP launched various projects in the thematic areas of governance and resistance, all of which are aligned with the SDGs. UNDP has a unique potential to leverage the development agenda through a number of initiatives on poverty reduction, livelihood, energy, environment and climate change, as well as crisis response and recovery, among the UN system’s projects. The UNDP’s resistance-related initiatives in newly merged areas of Khyber Pakhtunkhwa have assisted one million displaced individuals, accounting for 30 to 40% of the overall displaced population. Furthermore, government’s ownership of development priorities for the local community was fully ensured as a result of this intervention. On the Public Sector Development Programme, additional capacity building around financial management systems ensured monitoring and reporting based on real-time data. UNDP’s assistance in KP’s merged areas aided in resilience building, enhanced service delivery, and economic recovery. Infrastructure support and technical assistance in KP and Balochistan helped to improve public sector institutions, allowing for more effective and efficient service delivery. The Bar Council in KP benefited from the support, which has increased the number of women members from 160 in 2020 to 200 in 2021 (a 25 percent increase) and has helped additional women to enter the legal profession through scholarships. The KP Bar Council also assumed ownership of the 22 Legal Aid Desks as a move towards legal institutionalisation. With UNDP’s assistance, district resolution councils (DRCs) in Khyber Pakhtunkhwa were able to settle 68 percent of 3,454 cases they were assigned in 2021. The KP prosecution department was able to exhibit 3.8 percent rise in prosecution rate in 2021 compared to 2020 owing to UNDP’s assistance. Similarly, in Khyber Pakhtunkhwa, support to the judiciary resulted in a reduction in the acquittal rate of cases from 11.3 percent in 2019 to 10.6 percent in 2020. With UNDP’s assistance to the judiciary in capacity building and infrastructure, the case disposal rate in KP increased by 3% from 91 percent in 2020 to 94 percent in 2021. In order to have fast-track litigation, UNDP established 35 virtual courts and 75 virtual points in 22 districts of KP and 7 merged area districts under its digitization component with Peshawar High Court. Through the development of a human rights information management system, UNDP collaborated with the Ministry of Human Rights to make data collecting and reporting on human rights indicators smoother. The United Nations Development Programme also assisted the National Disaster Management Authority in aligning its policies with the Sendai Framework for Disaster Risk Reduction (CPD Outcome 2). It also worked with the Punjab government to include the climate change, biodiversity and ecosystem conservation into the provinces’ forest policy. With the Parliament taking the lead on the SDG agenda, UNDP was able to get the required backing to achieve the desired results in terms of SDG data monitoring and reporting in Pakistan. Technical assistance from the UNDP assisted the government in presenting its SDG portfolio at global level and in launching the Nature Performance Bond initiative. Through collaboration with the China International Centre for Technical Exchanges, UNDP’s support was vital in securing new funding sources for SDG acceleration in Pakistan. With UNDP’s support, the Provincial Disaster Management Authorities (PDMAs) in Sindh, KP, and Punjab were able to develop disaster risk reduction and climate change adaptation plans. The UNDP enabled the Pakistan Meteorological Department (PMD) build and develop the early warning systems, as well as train local volunteers to monitor glaciers in KP and GB. The UNDP also assisted the Punjab government in implementing landscape ecosystems in the province. Major Lessons Learnt: - Women’s mobility in the newly merged areas of KP and rural areas of Balochistan is influenced by the cultural norms and practices. This necessitates a greater focus on the reasons of such small-scale activities aimed at women. Limitations imposed by local culture and conventions have a significant impact on the success of women-focused interventions. However, a thorough examination of the problem and how to address it in future is required. - Alternate Dispute Resolution forums and Dispute Resolution Committees, if fully employed, can help to ease the strain of the formal legal systems. According to the Khyber Pakhtunkhwa Police Act of 2017, these DRCs must be constituted at the tehsil and UC levels to be completely functioning. More women must be represented in the structures in order for them to be accessible to women. - Several lessons acquired from project-based evaluation studies should be incorporated into Stories of Change, which link these to the theory of change (ToC). Declaring Islamkot, Sindh as the model SDG taluka, for example, can be replicated in other regions and provinces. Learning from private-sector collaborations, such as the Pakistan Stock Exchange’s adoption of SDG reporting for listed companies, has the potential to be scaled up to other private-sector organizations. The Government’s action plan for Green Sukuk energy funding and the problem sit faced in implementing it could be useful in devising similar interventions in the future for medium to long-term financing needs. - Gender was generally seen as cross cutting across all of the interventions. Women were seen as beneficiaries in most programmes, with the exception of handful. The necessity of mainstreaming gender throughout programmes for gender equality and women empowerment is highlighted in the UNDP Strategic Plan 2018 -2021. Within the framework of SDG5, the UNDP Pakistan Country Office must additionally invest in expanding resources for gender mainstreaming across interventions, promoting women’s leadership and advancing the inclusion agenda. There is also a need to explore approaches such as ‘reaching women at the household level’, and ‘gaining access to women through awareness sessions’, in the merged areas in terms of benefits and drawbacks of these approaches in order to learn from them in future interventions. - The early warning system procurement process for GB and KP was delayed, and as a result, the procurement of the technical equipment could not be completed on time, causing delays in related activities. At the design stage, these processes should be given significant consideration. - The government’s low resource allocation for SDGs programmes remained a major challenge for UNDP, delaying programmatic activities. To prevent delays caused by sole reliance on the government’s cost sharing agreements, the private sector could be involved in the future as a prospective partner in cost-sharing arrangements. - The UNDP must establish itself as a major player in climate resilience, based on the implementation of a wide range of technical initiatives and a long-term collaboration with the MOCC. It must prioritise the protection of local people’s livelihoods, particularly women’s, while also including technological innovation, harvesting green energy initiatives based on solar energy, and water conservation through rainwater collection.

III. Country Programme Resources

| Focus Area | Programme Expenditure ($) |  |  | % of Total |
| --- | --- | --- | --- | --- |
|  | Regular (TRAC) | Other | Total |  |
| Democratic Governance | 971,134 | 42,393,443 | 43,364,577 | 40.65% |
| Poverty and SDGs | 544,078 | 1,877,211 | 2,421,289 | 2.27% |
| Crisis Prevention and Recovery | 937,776 | 34,313,361 | 35,251,137 | 33.04% |
| Environment and Sustainable Development | 440,195 | 25,205,634 | 25,645,829 | 24.04% |
| Total | 2,893,183 | 103,789,649 | 106,682,832 |  |

Data sources: (please indicate the main sources from which data were obtained for this report.)

- German Watch, 2021, Global Climate Risk Index available Germanwatch - Gul, Shirin, 2021, Mid-Term Review, Institutional Support to Climate Change Adaptation and Mitigation, UNDP Pakistan - Husain, Tariq, 2020, Mid-Term Evaluation of National Initiative for Sustainable Development Goals - Khan, Bilal Hassan, 2021, Mid Term Evaluation of UNDP’s Decentralization Human Rights and Local Governance (DHL) Project, UNDP Pakistan - Open Budget Index 2019, available IBPJ7383-Open-Budget-Survey-Ranking standalone-Outlined-v2 (internationalbudget.org) - Project Implementation Review (PIR), 2020, ‘Sustainable forest management to secure multiple benefits in Pakistan's high conservation value forests (SFM) - SEBCON, Final Report, 2021, Final Evaluation of Phase I of the Stabilisation and Development Programme (SDP) - Former FATA Transition and Recovery Programme (FTRP) - Sustainable Development Policy Institute, 2019, Impact Evaluation of Strengthening Rule of Law Programme (SRLP) - The Status Report 2019 on Disaster Risk Reduction, 2019, available: 68260_682307pakistandrmstatusreport.pdf (preventionweb.net) - UNDP Human Development Report, 2018 - UNDP, 2018, Results Oriented Annual Report, UNDP Pakistan - UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan - UNDP, 2019, Results Oriented Annual Report, UNDP Pakistan - UNDP, 2020, Pakistan National Human Development Report 2020, available: Pakistan National Human Development Report on Inequality ¦ UNDP in Pakistan - UNDP, 2020, Results Oriented Annual Report, UNDP Pakistan - United Nations Development programme, 2018, Gender Equality Strategy 2018-2021 available: UNDP Gender Equality Strategy 2018-2021.pdf - United Nations Development Programme, 2018, UNDP Country Programme Document (2018-2022) - United Nations Development Programme, 2021, UNDP Evaluation Guidelines (Revised edition June 2021), available: UNDP_Evaluation_Guidelines.pdf - United Nations Evaluation Group, 2017, UNEG Norms & Standards for Evaluation (English version, 2017) available: Detail of Norms and Standards for Evaluation (2016) (unevaluation.org) - United Nations Sustainable Development Group, UNCT-SWAP Gender Equality Scorecard, available: UNCT-SWAP_Gender-report_Web.pdf - Wong, Roland, 2020, Terminal Evaluation of UNDP/GEF Project: 6th Operational Phase of the GEF Small Grants Programme in Pakistan (SGP 6), UNDP, Pakistan

This assessment of results is to be prepared only in the absence of a completed Independent Country Programme Evaluation (ICPE) for the cycle.

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

UNDP, 2019, Result Oriented Annual Report (ROAR)

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

German Watch, 2021, Global Climate Risk Index, available: Germanwatch

This indicator cannot be directly measured because no survey data is available

Based on the information available: National Assembly of Pakistan

The global percentage of women parliamentarians is 25.6 indicating the gap of 5.1 percentage points. Further details about the global percentage, available: Proportion of seats held by women in national parliaments (%) | Data (worldbank.org)

Findings are based on the survey results reported in the 2019 Results Oriented Annual Report (ROAR) by UNDP Pakistan

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

The local government elections were supposed to take place in 2019, but they were postponed. On December 19, 2021, the first phase of elections in KP was held in 17 districts

Khan, Bilal Hassan, 2021, Mid Term Evaluation of UNDP’s Decentralization Human Rights and Local Governance (DHL) Project, UNDP Pakistan

Pakistan was among the ten most affected countries in the ‘Long-term climate risk index’ from 2000 to 2019, according to the German Watch 2021 Global Climate Index, with 0.52 percent economic losses per unit GDP available: Germanwatch

Gul, Shirin, 2021, Mid-Term Review, Institutional Support to Climate Change Adaptation and Mitigation, UNDP Pakistan

Meaning ‘Successful Youth’ (in Urdu language)

UNDP, 2018, Results Oriented Annual Report (ROAR), UNDP Pakistan

UNDP, 2020, Results Oriented Annual Report (ROAR), UNDP Pakistan

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

Project Implementation Review (PIR), 2020, ‘Sustainable forest management to secure multiple benefits in Pakistan's high conservation value forests (SFM)’

Wong, Roland, 2020, Terminal Evaluation of UNDP/GEF Project: 6th Operational Phase of the GEF Small Grants Programme in Pakistan (SGP 6), UNDP, Pakistan

The findings in this section are based on the review of 13 Project Evaluation Reports? and three CPD 2018 - 2022 Result Oriented Annual Reports (ROAR) for Pakistan.? UNDP Country Office Pakistan implemented five projects under Outcome 1 and eight projects under Outcome 2

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

UNDP, 2018 - 2021 Strategic Plan, Results Oriented Analysis Report, Final Draft for OPG Review, UNDP Pakistan

SDPI, 2019, Impact Evaluation of Strengthening Rule of Law Programme (SRLP) in Selected Districts of Khyber Pakhtunkhwa

Focus area of the Country Programme 2018-2022 for Pakistan