**ANNEX**. **FULLY COSTED EVALUATION PLAN**

|  |
| --- |
| **Comments:** This evaluation plan covers the initial period of 2023-2027 and was developed with the participation of the national counterpart. In addition to the UNDP evaluation policy, it also considers lessons learned from the implementation of the evaluation plan of the previous program and innovations in program implementation (portfolio approach). In addition to the compulsory evaluations of projects initiated during the previous programme, it contains a portfolio evaluation, a mid-term evaluation of the CPD covering all the outcomes. Its implementation will strengthen accountability to government and donors by paying particular attention to mandatory evaluations as defined in the UNDP Evaluation Policy and Guidelines.  During the implementation, emphasis will be placed on progress in achieving the results defined in the main strategic documents such as the National Recovery and Peacebuilding Plan (RCPCA), the United Nations Sustainable Development Cooperation Framework (UNSDCF) and the UNDP Strategic Plan 2022-22025. Emphasis will also be placed on the evaluation of gender mainstreaming. |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **UNDAF (or equivalent) Outcome** | **UNDP Strategic Plan Outcome** | **Evaluation Title** | **Partners (joint evaluation)** | **Evaluation commissioned by (if not UNDP)** | **Type of assessment** | **Planned Evaluation Completion Date** | **Estimated Cost** | **Provisional Source of Funding** |
| All CPD outcomes | Outcome 1 Outcome 2 Outcome 3  Outcome 4 | Mid-term evaluation of CPD | UNDP  Government  MINUSCA UNICEF GEF UN Women | N / A | Programme | November 2025 | $50,000 | M&E budgets |
| Outcome 1: By 2027, people in the CAR live under the rule of law, have access to justice and security, and their human rights are promoted and protected. | Outcome 1 | Terminal evaluation of the project "Electoral Process Support Project in the Central African Republic" | UNDP  Government  MINUSCA | N / A | Project | March 2024 | $40,000 | Project budget |
| Outcome 3: By 2027, people in CAR live in an environment where peacebuilding, national reconciliation, and governance mechanisms are inclusive, accountable, and effective | Outcome 3 | Terminal evaluation of the project "Defenders of human rights actors of the consolidation of peace" | UN Women UNDP  Government | N / A | Project | March 2023 | $30,000 | Project budget |
| Outcome 1: By 2027, people in the CAR live under the rule of law, have access to justice and security, and their human rights are promoted and protected. | Outcome 1 | Terminal evaluation of the project "Support for the functioning of the Special Criminal Court" | MINUSCA  UNDP  Government | N / A | Project | June 2024 | $40,000 | Project budget |
| Outcome 1: By 2027, people in the CAR live under the rule of law, have access to justice and security, and their human rights are promoted and protected. | Outcome 1 | Terminal evaluation of Rule of law portfolio | UNDP  Government  MINUCA  EU  UN Women  PBF | N/A | Portfolio | November 2025 | $50,000 | Portfolio budget |
| Outcome 1: By 2027, people in the CAR live under the rule of law, have access to justice and security, and their human rights are promoted and protected. | Outcome 1 | Terminal project evaluation of the project “Renforcement of the rule of law» | UNDP  Government  MINUSCA | N / A | Project | June 2025 | $50,000 | Project budget |
| Outcome 3: By 2027, people in CAR live in an environment where peacebuilding, national reconciliation, and governance mechanisms are inclusive, accountable, and effective | Outcome 2 | Terminal evaluation of the project "Support for fragility and local development» | UNDP  Government | N / A | Project | March 2026 | $40,000 | Project budget |
| Outcome 3: By 2027, people in CAR live in an environment where peacebuilding, national reconciliation, and governance mechanisms are inclusive, accountable, and effective | Outcome 2 | Final evaluation of the project Local Development and Resilience» | UNDP  Government | N / A | Project | June 2023 | $5,000 | Project budget |
| Outcome 3: By 2027, people in CAR live in an environment where peacebuilding, national reconciliation, and governance mechanisms are inclusive, accountable, and effective | Outcome 2 | Final evaluation of the project "Support for durable solutions for displaced or returned persons and their host communities as well as for children released from armed groups in the prefectures of Ouham-Pende and Basse Kotto" | UNDP  Government  UNICEF | N / A | Project | March 2023 | $40,000 | Project budget |
| Outcome 4: By 2027, the resilience of the State and populations is strengthened through the sustainable governance of natural resources and the environment | Outcome 4 | Terminal evaluation of the project “Promotion of Small Hydropower Plants” | UNDP  Government  GEF | N / A | Project | March 2024 | $5,000 | Project budget |