## UNCDF-2014 Reccomendations
Rec No | para | Key Recommendation | Primary Owner | Priority | Audit Action plan | Implementation Status as of October 2014 | Target Completion date
1 | 19 | UNCDF agreed with the Board recommendation to work closely with UNDP to gain access to the tools and platforms and effectively utilize them for strategic planning, monitoring and reporting of its programmes and activities to deliver better results. | Directorate | Medium | UNCDF is currently working with UNDP to effectively use the available platforms and tools for planning, monitoring and reporting, and where necessary, UNCDF will develop its own tools based on its unique requirements | In progress | Q2,2016
2 | 23 | UNCDF agreed with the recommendation to ensure that all offices prepare procurement requisitions plan, and the plans are consolidated in line with Programmes Operations Policies and Procedures requirements. | Management Support Unit | High | In January 2015 UNCDF implemented an online tool for Country Offices to upload their consolidated procurement plans. The plans will be regularly updated and the uploading of plans monitored. | Implemented | Q1,2015
3 | 27 | UNCDF agreed with the Board’s recommendation to (a) continue strengthening the oversight mechanism to ensure that Performance Management Development plans and assessments are completed in a timely manner, reviewed and approved by respective managers, and (b) develop a clear action plan in collaboration with UNDP to ensure that PMD is used in talent management and assessment of results, competency domains and staff capacity | Directorate | High | Management agrees to (a) establish an oversight mechanism to ensure PMDs are completed on a timely basis; and (b) Work with the talent management group within OHR to ensure annual PMD results are used in talent management and assessment of staff capacity. | In progress | Q4,2015
4 | 31 | UNCDF agreed with the recommendation to (a) expedite the process of operational closure for all projects based on their projects ending dates and review the project status in Atlas in a timely manner to comply with POPP, (b) the Investment Committee and UNDP/UNCDF speed up the process of approving the budgets at inception to allow MPTF’s approval of their budget to facilitate implementation of activities under Phase II projects. | Directorate | Medium | UNCDF will endeavour to (a) close projects on a timely basis in line with project end dates; and (b) approve budgets in line with project start dates. | In progress | Q4,2015
5 | 36 | UNCDF agreed with the Board’s recommendation to (a) liaise with donors to agree a mechanisms in future trust fund agreements to dispose of any remaining balances; (b) establish timelines and take all necessary measures to refund or re-programme $1.3 million from 22 inactive trust funds; and (c) expedite the process of financial closure of all long outstanding operationally closed projects and review in a timely manner the project status in Atlas to comply with policies and procedures in operational and financial closure of projects. | Directorate | Medium | On (a) The exiting standard agreements have a clause on mechanisms to dispose of any remaining balances; on (b) a new program management support unit will monitor and process refunds or re-programme funds from inactive trust funds; and on (c) take action to close inactive projects in line with POPP. | In progress | Q4,2015
6 | 40 | UNCDF agreed with the Board’s recommendation to (a) enhance follow-up of the grantees to ensure that they meet milestones and budgeted grants are issued in a timely manner, (b) ensure that no MFI is approved to carry out UNCDF operations and to receive grants without having valid licenses and fulfilling host country operational requirements; (c) adhere to the signed financing agreements and disbursement conditions; and (d) promptly collect the funds from grantees who fail to meet the agreed conditions. | Financial Inclusion Practice Area (FIPA) | Medium | UNCDF will (a) enhance monitoring of grantees and ensure appropriate approvals for delaying the initiation of reimbursement of funds as per grant agreement; on (b) Ensure that MFIs do not commence the provision of financial services without having appropriate licenses or government endorsement for pilots in place; on (c) Monitor adherence to disbursement conditions in the signed financing agreement; and (d) In instances where grantees fail to meet the agreed conditions, notify the grantee and assess the feasibility of recouping funds in line with the terms of the agreement. | In progress | Q4,2015
7 | 44 | UNCDF agreed with the recommendation that Fiji Regional office comply with Programmes Operations Policies and Procedures to ensure that (a) Performance indicators; baseline and targets are established at each country office for each output of the projects so as to come up with Regional level impact, outcome, baseline, indicators and targets; (b) include the annual output targets in AWP of projects which would serve as the reference points in the corporate results monitoring systems; and (c) all annual work plans are prepared and approved by the committee, signed and dated. | Financial Inclusion Practice Area (FIPA) | Medium | UNCDF Fiji Regional office agrees to (a) Establish performance indicators at the appropriate levels required for monitoring results; (b) Include the annual output targets in the AWP; and (c) Prepare, approve and sign AWPs on a timely basis in line with UNCDFs planning calendar | In progress | Q4,2015
8 | 47 | The Board recommends that UNCDF align the activities involved in project budgeting and execution to ensure efficient and timely delivery of targeted project budget performance. | Directorate | Medium | UNCDF will ensure alignment of project budgeting and implementation to ensure timely delivery of targeted project budget performance. | In progress | Q4,2015
9 | 50 | UNCDF agreed with the recommendation to perform analysis to: (a) substantiate the reserve amount in terms of percentage, to establish its reserve in line with the Risk Mitigation Strategy or Framework component; and (b) establish the method for calculation of reserves to mitigate risks associated with cost sharing and trust funds with respect to expenditure-related risks, structural risks and liability risks for further Executive Board approval | Directorate | High | UNCDF will carry out an analysis of its reserve levels and calculation methodology in line with current risk framework. | In progress | Q2,2016