**CPD Evaluation Plan 2023-2025**

**UNDP Country Office**

**Libya**

The UNDP Libya CPD Evaluation Plan is an important accountability and learning instrument for the Country Office and stakeholders. It is designed as a strategic tool to inform decision-making at both project and programme levels. The plan describes the intended evaluations over the period 2023-2025 along with associated costs. It contains a mix of midterm and terminal project, thematic and outcome level evaluations across the country Programme as a whole to measure the extent to which UNDP Libya is contributing to change at both national and Local levels. The UNSDCF and CPD planification process highlighted the need for evidence-based information on UN/UNDP contribution to national goals.

The CPD Evaluation plan foresees nine evaluations during the next 3 years as per the following table. There are 4 evaluations in 2023 of which 2 are from pervious cycle and is mandatory.

The current evaluation plan is planning:

1 CPD Outcome and 1 thematic evaluation:

A outcome evaluation of the Country Programme will be conducted in 2025 that will generate key information on the successes, challenges, lessons learned to inform the preparation of the future Country Programme in particular on new environment portfolio. Thematic evaluation on gender will also be conducted for better gender based programming.

Projects evaluation:

For future projects approved within the framework of the new cycle, relevant evaluations will be integrated in the Evaluation Plan as they arise, in compliance with UNDP regulations.

The evaluation plan will be reviewed on a yearly basis to verify that the planned project evaluations in particular could indeed take place at the expected time and any required adjustments would be indicated to the concerned focal point at regional office. CO will ensure constraint factors are fully considered during annual planning and implementation.

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S.no | UNSCDF/CPD Outcome | Strategic Plan outcome | Evaluation Title | Partners (joint evaluation) | Evaluation commissioned by (if not UNDP) | Type of evaluation | Planned Evaluation Completion Date | Estimated Cost ($US) | Provisional Source of Funding |
| 1 | Outcome 4  By 2025, all people in Libya, especially the most vulnerable and marginalized, have increased resilience to the impacts of climate change and environmental degradation, including through improved and equitable access to climate-resilient water, sanitation, and hygiene services, and clean and renewable energy sources. | Outcome 1, 2 and 3 | Outcome evaluation of CPD (2023-2025) |  | UNDP | Outcome Evaluation | May 2025 | 50,000 | Project Budget |
| 2 | Outcome 1.1, 1.2 and 4 | Outcome 1, 2 and 3 | Thematic evaluation on Gender |  | UNDP | Thematic Evaluation | May 2025 | 50,000 | Project Budget |
| 3 | Outcome 1.1 By 2025, all people in Libya, particularly the most vulnerable, are freely able to exercise their rights and obligations in an inclusive, stable, democratic, and reconciled society, underpinned by responsive, transparent,  accountable unified public institutions. (SDGs # 5, 8, 10, 16, 17) | Outcome 2 | Mid Term Evaluation of ‘promoting Elections for the People of Libya (PEPOL) (2018-22) |  | UNDP | Project Evaluation | February 2023 | 30,000 | Project budget |
| 4 | Outcome 1.1 By 2025, all people in Libya, particularly the most vulnerable, are freely able to exercise their rights and obligations in an inclusive, stable, democratic, and reconciled society, underpinned by responsive, transparent,  accountable unified public institutions. (SDGs # 5, 8, 10, 16, 17) | Outcome 2 | Terminal Evaluation of ‘Promoting Elections for the People of Libya (PEPOL)- Phase-II (2023-25) |  | UNDP | Project Evaluation | November 2024 | 30,000 | Project |
| 5 | Outcome 1.2: By 2025, all people in Libya participate in and benefit from a more peaceful, safe, and secure society, free from armed conflict and underpinned by unified and strengthened security, justice, rule of law, and human rights institutions that promote and protect human rights based on the principles of inclusivity, non-discrimination, and equality in accordance with international norms and standards.  (SDGs # 5, 8, 10, 16, 17) | Outcome 2 | Terminal Evaluation of UNSMIL/UNDP Policing and Security Joint Programme (PSJP) - Phase-II |  | UNDP | Project Evaluation | November 2025 | 30,000 | Project |
| 6 | Outcome 1.1:  By 2025, all people in Libya, particularly the most vulnerable, are freely able to exercise their rights and obligations in an inclusive, stable, democratic, and reconciled society, underpinned by responsive, transparent,  accountable unified public institutions.  (SDGs # 5, 8, 10, 16, 17) | Outcome 2 | Terminal Local Elections Project Evaluation |  | UNDP | Project Evaluation | August 2023 | 30,000 | Project |
| 7 | Outcome 1.2: By 2025, all people in Libya participate in and benefit from a more peaceful, safe, and secure society, free from armed conflict and underpinned by unified and strengthened security, justice, rule of law, and human rights institutions that promote and protect human rights based on the principles of inclusivity, non-discrimination, and equality in accordance with international norms and standards (SDGs # 5, 8, 10, 16, 17) | Outcome 1,3 | Mid Term Evaluation of “Recovery, Stability and Socio-economic Development in Libya”. |  | UNDP | Project Evaluation | January 2023 | 30,000 | Project |
| 8 | Outcome 1.2:  By 2025, all people in Libya participate in and benefit from a more peaceful, safe, and secure society, free from armed conflict and underpinned by unified and strengthened security, justice, rule of law, and human rights institutions that promote and protect human rights based on the principles of inclusivity, non-discrimination, and equality in accordance with international norms and standards.  (SDGs # 5, 8, 10, 16, 17) | Outcome 1&3 | Terminal Evaluation of “Recovery, Stability and Socio-economic Development in Libya II”. |  | UNDP | Project Evaluation | October 2024 | 30,000 | Project |
| 9 | Outcome 4 By 2025, all people in Libya, especially the most vulnerable and marginalized, benefit from improved, equitable, and more sustainable access to better managed and preserved natural resources, climate-resilient water, sanitation, and hygiene services, and promote green growth that is risk-informed, including the provision of clean and sustainable energy (SDGs # 3, 6, 7, 8, 9, 11, 13, 14, 17) | Outcome 1, 3 | Terminal Evaluation of Energy Project |  | UNDP, GEF | Project Evaluation | November 2023 | 30,000 | Project |