## 2014 UNDP details
No | Functional Area | Para | Key Recommendation | Primary Owner | Secondary Owner | Priority | Audit action plan | Implementation Status as of September 2015 | Target Completion Date
1 | Financial Mgmt. | 23 | UNDP agreed with the Board recommendations to (a) ensure at year-end, COs/HQ Units review the report of contracts with pending milestones and, for any identified issue, communicate to the GSSC via the DMS and update the status accordingly; and (b) make follow-up with the country offices/HQ units such that, previous’ years pending milestones (from 2011 to 2014) are cleared without further delays. | OFRM | OFRM | Medium | On (a) UNDP will ensure that procedures in place for the review and monitoring of pending milestones are complied with and timely action is taken; on (b), UNDP will request offices to promptly follow-up outstanding balances with donors and notify GSSC of any changes to the schedule of payments that are required under existing procedures. | In Progress | Q1,2016
2 | Financial Mgmt. | 27 | UNDP agreed with the Board’s recommendations to: (a) request country offices to promptly follow-up on all outstanding balances with donors and notify GSSC of any changes to the schedules of payments that are required under existing procedures; (b) assess and maintain evidences of follow-up made with donors for long outstanding receivables; and (c) assess aged receivables and record impairment for cases where donor’s whose ability to pay is doubtful as per UNDP’s policy. | OFRM | OFRM | Medium | On (a) and (b), UNDP will request offices to promptly follow-up outstanding balances with donors and notify GSSC of any changes to the schedule of payments. Evidence of such follow up will be maintained and used for assessment of long outstanding receivables. On item (c), Impairment provisions will be established for specific contributions where the donor’s ability to pay is in doubt and there is a risk of financial loss to UNDP | In Progress | Q2, 2016
3 | Programme and project management | 30 | UNDP agreed with Board recommendations that (a) Papua New Guinea country office in collaboration with the UN country team should complete missing information on national indicators, source of data, baselines and assumptions; and (b) an annual review of UNDAF at Brazil be carried out in 2015 and the country office pursue timely signing of the CPAP by the Government. | RBAP/ RBLAC | RBAP/ RBLAC | Medium | On (a), UNDP Papua New Guinea in collaboration with the UN country team will use the ongoing review of the UNDAF Action Plan results framework, to update and complete missing information on national indicators, source of data, baselines and assumptions; on (b), Annual review of UNDAF in Brazil will be carried out from May 2015 onwards. And on (c), BRAZIL CO will continue to make all possible efforts in order to ensure that future CPAP is approved and signed by the Government in a timely manner. | In Progress | Q1,2016
4 | Programme and project management | 34 | UNDP agreed with the Board’s recommendation to ensure that Regional Bureaux monitor the assessment of NIM implementing partners in line with POPP and that all project monitoring activities are carried out and documented. | RBX | RBX | High | Regional Bureaux will monitor the assessment of NIM implementing partners in line with POPP and ensure that all project monitoring activities are carried out in line with the new results based management platform that enables monitoring results to be reflected in the system. | In Progress | Q4,2015
5 | Programme and project management | 38 | UNDP agreed with the Board recommendation that Argentina and Brazil country offices (a) use an updated TORs for NIM auditors, and (b) conduct capacity assessments of government auditors as per headquarters guidelines. | RBLAC | RBLAC | Medium | On (a), Argentina and Brazil will update the current standard OAI TORs for NIM audits with the government counterparts; and on (b), an updated capacity assessment for Brazil government auditors was delivered in October 2014. | In Progress | Q4,2015
6 | Programme and project management | 42 | UNDP agreed with Board recommendations that Argentina, Brazil and Papua New Guinea country offices collaborate with programme government counterparts to set realistic and attainable projects activities and budgets in line with available resources; and monitor implementation progress at the country level to minimize implementation delays and the need to reduce budgets at the year end. | RBAP/ RBLAC | RBAP/RBLAC | High | Argentina, Brazil and Papua New Guinea will establish realistic budgets for projects implemented with government counterparts and monitor implementation on a regular basis | In Progress | Q4,2015
7 | Programme and project management | 47 | UNDP agreed with Board recommendation that Country Offices prepare a resource mobilization implementation plan in compliance with the guidelines established in the resource mobilization toolkit. | RBX | BERA | Medium | Regional Bureaus will work with Country Offices to ensure that they comply with the guidelines of the resource mobilization toolkit and prepare resource mobilization implementation plans. | In Progress | Q3,2016
8 | Programme and project management | 50 | The Board reiterates its previous recommendation that UNDP submits the combined delivery reports in a timely manner, duly signed by UNDP and implementing partners in compliance with POPP. | RBX | RBX | Medium | Regional Bureaus will work with Country Offices to submit the CDRs in a timely manner, and ensure appropriate follow up of Implementing Partner signature. | In Progress | Q2,2016
9 | Programme and project management | 55 | UNDP agreed with the Board’s recommendations that, Country Offices: (a) prepare progress reports for all projects in a timely manner, and (b) perform and document all requirements for projects monitoring including the update of risks logs in Atlas and to conduct project board meetings. | RBX | RBX | High | In line with the project quality assurance system currently being rolled out in three phases, Regional Bureaus will work with COs to ensure that (a), progress reports are prepared on a timely manner; and (b), Requirements for project monitoring are documented including assurance for risk management and that project risks are recorded and regularly updated. | In Progress | Q2,2016
10 | Programme and project management | 59 | UNDP agreed with the Board recommendations to (a) exert more effort to financially close all projects which are in operationally closed status for more than 12 months; (b) ensure that appropriate projects completion checklists are completed, final CDR for financial closure of projects are generated and timely certified by responsible parties and final review reports are prepared consistently for operationally closed projects, (c) ensure projects’ Board meetings are conducted in a timely manner and projects are evaluated as planned, reconciliations of expenditure are certified and lesson learnt reports are prepared in a timely manner; and (d) make efforts to refund amount due to donors in line with POPP and donor agreements. | RBX | OFRM | High | UNDP will update its policies and guidelines with regards to project closure and evaluations in line with the recent developments in Quality Assurance during the project life cycle. In addition COs will be requested to designate focal points responsible to ensure project closure activities are carried out in line with POPP. | In Progress | Q4,2015
11 | HACT | 63 | UNDP agreed with the Board’s recommendations that (a) all country offices develop and implement comprehensive HACT assurance plans for performing macro and micro assessments in a timely manner considering their programmatic cycles; and (b) wherever there is a shared Implementing Partner, the joint HACT Working Groups should develop a comprehensive Joint HACT assurance plan which will cover all components highlighted in the POPP. | RBX | OFRM | Medium | UNDP specific guidance on HACT has been made available in POPP and includes the need to develop joint assurance plans where there is a shared Implementing partner and a joint HACT working group. Regional bureaus will work with COs to ensure to ensure timely completion of macro and micro assessments in line with programmatic cycles and POPP. | In Progress | Q2,2016
12 | Internal Control Issues | 68 | UNDP agreed with Board’s recommendation to (a) introduce timelines and robust quality assurance process for POPP updates, approval and implementation; and (b) ensures that POPP, IPSAS policies and other applicable guidelines have updated contents in line with stipulated timelines. | EXO | OFRM | High | UNDP will develop a monitoring mechanism to track timelines and robust quality assurance processes in respect of POPP policies (including IPSAS policies) updates, approval and implementation. | In Progress | Q4,2015
13 | Internal Control Issues | 74 | UNDP agreed with the Board’s recommendations to ensure that country offices comply with the segregation of duties for bank reconciliation, assets management and leave management in line with its Internal Control Framework. | OFRM | OFRM | Medium | Regarding segregation of duties for bank reconciliation, Internal Control Framework (ICF) conflicts among bank signatory, Country Offices will be requested to correct non-compliance when this is identified. On asset management, UNDP will send a reminder message to COs to ensure compliance with the ICF requirement. With regards to leave management, In February 2015 the organization moved away from using the manual attendance record cards. The new process ensures appropriate segregation of functions in line with the ICF | Implemented | Q4,2015
14 | Human Resources Management | 78 | UNDP agreed with the Board recommendation to (a) adhere to the service contract user guide on the proper use of the service contracts by ensuring that service contracts staff are recruited for only those functions and duties as stipulated in service contract user guide; and (b) amend the terms of contracts for service contracts to clearly define the support functions and duties of the service contracts. | OHR | OHR | Medium | On (a) UNDP will Monitor and report to relevant offices instances of non-compliance; refine the POPP content for better clarity and send reminder message to offices on the need for compliance with existing POPP requirements. On (b), UNDP will develop generic TORs for Service Contracts by the end of 2015 and will provide Country Offices with clearer guidance on the standards for developing Service Contract Terms of Reference aligned with the overall program results. | In Progress | Q2,2016
15 | Human Resources Management | 86 | UNDP agreed with the Board recommendation to (a) develop a clear action plan to ensure that PMD is used in talent management and assessment of results, competency domains and staff capacity; and (b) ensure country offices introduce an oversight mechanism such that PMD plans and assessments are completed in a timely manner, reviewed and approved by respective managers. | OHR | OHR | High | On (a), A number of refinements to the performance management approach and supporting tools will be delivered in 2015, ensuring closer linkage between performance management and other talent management processes and decisions; and on (b), UNDP will monitor compliance and ensure appropriate follow up through the regional and central Bureaux. | In Progress | Q1,2016
16 | Information Communication Technology | 90 | UNDP agreed with the Board’s recommendation that: (a) OIST adopts a framework for carrying out, documenting and integrating management of all IT-related risks (security, service delivery, project delivery etc.) into the overall UNDP Enterprise Resource Management; and (b) all units within OIST comply with the established unit level strategic planning process. | OIST | OIST | Medium | On (a), In line with the established framework which integrates IT risks into UNDPs ERM , OIST updated the risk logs in 2014, and will continue doing so; and on (b), all OIST units will continue to comply with the established unit level strategic planning process. | In Progress | Q4,2015
17 | Information Communication Technology | 95 | UNDP agreed with the Board’s recommendation to include in its contractual arrangements with UNICC the need and frequency of the report required under the International Standards on Auditing on Assurance Engagements (i.e. ISAE Type II reports) which will give reasonable assurance to both UNDP and the Board on the operating effectiveness of the UNICC controls within the annual financial reporting period. | OIST | OIST | High | UNDP agrees that a well-documented binding commitment by the UNICC on audit frequency is required and will discuss this matter with the UNICC to consider the best way of reflecting a binding commitment to the existing contract on the need and frequency of ISAE Type 2 audits. | In Progress | Q4,2015
18 | Programme and project management | 102 | UNDP agreed with the Board’s recommendation to (a) reconcile regularly performance indicators, baseline and targets contained in the annual work plans; and (b) supervise and monitor data quality, timing and completeness of information keyed in by country offices into the platform/tool of baseline, milestones and targets. | RBX | BPPS | Medium | On (a), the Corporate Baseline, Milestones and Targets (BMT) exercise was completed in December 2014, and a populated Integrated Results and Resources Framework (IRRF), with adjusted outputs and indicators, BMTs and actual results for 2014 has been finalized; and on (b), Regional Bureaus and Country Offices will use the new enhanced RBM platform, for monitoring quality, timeliness and completeness of data. | In Progress | Q1, 2016
19 | Procurements and Contracts Management | 105 | The Board recommends that UNDP: (a) investigate the errors in the process of reinstatement of POs balances ; (b) institute quality assurance mechanisms for Atlas External Access when reinstating the POs (c) Ensure a mandatory reference field is completed for reinstated purchase orders carried over from prior periods; and (d) ensure compliance with POPP requirements on raising separate POs for goods and services expected to be received in the respective financial periods | RBX | PSO | Medium | On (a) UNDP is only aware of errors identified in Brazil country office and is not aware of any errors from other Country Offices, errors from Brazil CO have been investigated; on (b), UNDP will support country offices in ensuring quality assurance mechanisms are in place to mitigate against the risk of errors during the process of reinstating POs with balances with respect to external access partners; on (c) UNDP will explore the feasibility of making the PO reference field mandatory; and on (d) UNDP will remind offices to follow POPP requirements | In Progress | Q4,2016
20 | Financial Mgmt. | 108 | UNDP agreed with the Board’s recommendation to: (a) liaise with UN entities and conclude term of references to the Office of the Ombudsman services and reach final agreement; and (b) work with UN entities and arrive at the agreed milestones for clearing long outstanding unresolved balances. | OFRM | OFRM | Medium | UNDP is actively working on clearing the unresolved balances with the respective UN entities and will follow up with the UN specifically with reference to the Office of Ombudsman service costs. | In Progress | Q1,2016
21 | Assets Management (PP&E and Inventories) | 113 | UNDP agreed with the Board’s recommendations that (a) Papua New Guinea and Myanmar country offices dispose of all assets which have been retired from use in a timely manner; and (b) de-recognize in the books/ISR all the assets which have already been physically disposed of and those which have been transferred to the Government. | RBAP | ASD | Medium | UNDP will follow up with the two offices to ensure timely disposal of assets not in use and recording of all transfers and disposals with the GSSC. | In Progress | Q2,2016
22 | Financial Mgmt. | 118 | UNDP agreed with the Board’s recommendations to revisit the regular resources operational and other resources reserve calculation methodology and identify possible alternatives taking into account (a) current UNDP operations; (b) current strategic plan and risk management framework; (c) the impact of the IPSAS framework on the calculation of the reserve and (d) the ongoing structural change. | OFRM | OFRM | High | UNDP will revisit its current operational reserve methodology and calculations to ensure that it takes into account recent changes to operational, strategic, risk management, accounting and structural frameworks. | In Progress | Q1,2016
23 | Structural Change | 124 | UNDP agreed with the Board’s recommendations to: (a) prepare a formal structural change benefit realization plan including lessons learnt so far, and (b) ensure monitoring mechanisms are used so that long term benefits are sustained in line with the formal benefit realization plan. | EXO | EXO | High | UNDP will prepare a benefits realization plan including lessons learnt and monitor the plan. | In Progress | Q4,2015
24 | Structural Change | 129 | UNDP agreed with the Board’s recommendations to (a) monitor and address staff complaints, claims or concerns over structural change from all channels including those from the staff council and facilitate their timely clearance to avoid reputational damage to UNDP; (b) strengthen opportunities for open, constructive dialogues and communications with staff and staff council in the ongoing structural changes; and (c) Establish plans for team buildings and staff motivation for confidence rebuilding; and embed a culture that motivates and sustains the structural change. | EXO | EXO | High | On (a) UNDP will monitor and address staff complaints from all channels including those from the staff council; on (b) continue to facilitate regular meetings with the Staff Council to discuss issues on structural change processes and on (c) Review each Bureau’s plan to move towards a more empowered, collaborative and innovative culture and monitor progress twice yearly. | In Progress | Q4,2015