Costed Evaluation plan

| UNDAF/CPD Outcome | Strategic Plan Results Area | Evaluation Title | Partners (joint evaluation) | Evaluation Commissioned by (if not UNDP) | Type of evaluation | Planned Evaluation Completion Date | Estimated Cost (USD) | Provisional Source of Funding |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Social and economic development of rural areas aimed at poverty reduction in rural areas | Sustained economic growth, poverty reduction, and social development | Social and economic development and poverty reduction outcome evaluation | None | - | Mandatory Outcome evaluation | March 31, 2014 | 30,000 | UNDP core programme resources |
| Improved access to and utilization of quality health, education and social services | Sustained economic growth, poverty reduction, and social development | Improved access to quality health, education and social services outcome evaluation | UNAIDS | - | Mandatory Outcome evaluation | November 30, 2014 | 40,000 | UNDP core programme resources |
| More effective and accountable public institutions respond to the needs of all persons within the jurisdiction of Ukraine, especially the most vulnerable | Governance and local development | Improved efficiency and accountability of public institutions outcome evaluation | None | - | Mandatory Outcome evaluation | October 31, 2015 | 30,000 | UNDP core programme resources |
| Government facilitates the participation of women in public, economic and political life | Governance and local development | Gender equality outcome evaluation | UNFPA | - | Mandatory Outcome evaluation | November 30, 2013 | 30,000 | UNDP core programme resources |
| Government of Ukraine adopts policy frameworks and mechanisms to ensure reversal of environmental degradation, climate change mitigation and adaptation, prevention and response to natural and man-made disasters | Environment and climate change | Climate change mitigation and environment protection outcome evaluation | None | - | Mandatory Outcome evaluation | July 31, 2015 | 40,000 | UNDP core programme resources |
| Project Evaluations |
| Government of Ukraine adopts policy frameworks and mechanisms to ensure reversal of environmental degradation, climate change mitigation and adaptation, prevention and response to natural and man-made disasters | Environment and climate change | Energy Efficiency, Lighting | GEF | _ | Mandatory project mid-term evaluation | 30 July 2013 | 20,000 | Project budget |
|  |  | Energy Efficiency, Lighting | GEF | _ | Mandatory project final evaluation | 30 September 2015 | 20,000 | Project budget |
|  |  | Energy Efficiency in Public Buildings | GEF | - | Mandatory project mid-term evaluation | 30 September 2014 | 20,000 | Project budget |
|  |  | Energy Efficiency in Public Buildings | GEF | - | Mandatory project final evaluation | 31 July 2016 | 20,000 | Project budget |
|  |  | Development and Commercialization of Bioenergy Technologies | GEF | - | Mandatory project mid-term evaluation | 20 July 2014 | 20,000 | Project budget |
|  |  | Development and Commercialization of Bioenergy Technologies | GEF | - | Mandatory project final evaluation | 30 October 2016 | 20,000 | Project budget |
|  |  | Improved Forest Management System in Mountain Forests | GEF | - | Mandatory project mid-term evaluation | 30 October 2014 | 20,000 | Project budget |
|  |  | Improved Forest Management System in Mountain Forests | GEF | - | Mandatory project final evaluation | 30 November 2016 | 20,000 | Project budget |
| Improved access to and utilization of quality health, education and social services | Sustained economic growth, poverty reduction, and social development | Community based approach to local development | EU | - | Non-mandatory mid-term project evaluation | 30 December 2012 | 20,000 | Project budget |
|  |  | Community based approach to local development | EU | - | Non-mandatory final project evaluation | 30 December 2014 | 30,000 | Project budget |
| System of strategic planning improved as a result of the introduction of MDG-based strategic governance | Governance and local development | Outputs and outcomes evaluation of the RDA support project | EU | - | Non-mandatory output and outcome evaluation | 20 December 2012 | 30,000 | Project budget |
|  | Governance and local development | Outputs and outcomes evaluation of Human Security Monitoring & Public Dialogue Project | None | - | Non-mandatory output and outcome evaluation | 31 January 2013 | 20,000 | Project budget |